## Task Schedule
QUALITYSOFT TEAM SCHEDULE
This schedule does not include any changes made after teleconference with professor on 3/4/13.
Please note that due to time constraints, we will not always be able to get professor feedback.
Drafts will be submitted to Elaine as per our schedule (which is far ahead of hers) and we will update our work as we receive feedback from her, but we will not wait for it.
The team schedule may not be submitted before its due date as defined under each task.
# | Job Name | Day of Week | Date Due | Time Due | Person Responsible | Predecessor | Date and Time Completed | Person Completing | Notes
https://sites.google.com/site/organizeyourteam/tasks-and-assignments/requirements
1.1 | Write up team contract | Sunday | 2013-03-03 | 11am | All (at mtng) | None | 10am 3/3/13 | All
1.2 | Review team contract | Sunday | 2013-03-03 | 11am | All (at mtng) | 1 | 10am 3/3/13 | All
1.3 | Write up team schedule | Sunday | 2013-03-03 | 6pm | Elena | 1 |  | Elena
1.4 | Review team schedule | Sunday | 2013-03-03 | 9pm | Satyen, Anaga | 2 |  | All
1.5 | Deliver: Team Schedule. 9AM | Monday | 2013-03-04 | 9am | Elena | 2 |  | Elena
1.6 | Deliver: Team Contract. 9AM | Monday | 2013-03-04 | 9am | Elena | 1 |  | Elena
https://sites.google.com/site/organizeyourteam/tasks-and-assignments/requirements
2.1 | Implement Git | Tuesday | 2013-03-05 | 8pm at mtng | all (at mtng) | Task 1 | 3/5/13 8pm | all
2.2 | If Git fails, implement a different way to share code | Tuesday | 2013-03-05 | 8pm at mtng | all | 7 | n/a | n/a
2.3 | Research how to store these class objects (class ArrayList?) | Wednesday | 2013-03-06 | as needed | Elena | Task 1 | ongoing | Elena | will be necessary next week
2.4 | Research how to search these objects for certain strings | Wednesday | 2013-03-06 | as needed | Satyen | Task 1 | ongoing | Satyen | will be necessary next week
2.5 | Additional Research if necessary | Wednesday | 2013-03-06 | as needed | Elena, Satyen | 11 | x | x | no formal research done
2.6 | Class Skeletons | thursday | 2013-03-07 | 16:30 | Elena, Anaga | 8, 9, 10 | 3/8/13 3am | Elena, Anaga
2.7 | Standard Class List | thursday | 2013-03-07 | 8am | Satyen | 11 | 3/7/13 6pm | Satyen
2.8 | Fake Run Recording | thursday | 2013-03-07 | 8am | Anaga | 11 | 3/8/13 3am | Elena
2.9 | Compile Design Document from parts | thursday | 2013-03-07 | 6pm | Satyen | 11, 12, 13 | at mtng | Satyen
2.1 | Review Design Document | thursday | 2013-03-07 | 10pm | Elena, Anaga | 14 | at mtng | Elena, Anaga | will also review on 3/8/13 in the AM
2.11 | Deliver: Design Document Draft | Friday | 2013-03-08 | 9am | Elena | 15 |  | Elena
| email elaine re: submission | Friday | 2013-03-08 | 9am | Satyen
2.12 | Review and Edit Design Document after Elaine’s comments | sunday | 2013-03-10 | 6pm | Satyen, Anaga | 16 | 2013-03-11 | Satyen, Anaga
2.13 | Elena will be back in town and will review | sunday | 2013-03-10 | 9pm | Elena | 17 | 2013-03-11 | Elena
2.14 | Deliver: Final Design Document | monday | 2013-03-11 | 8am | Satyen | 17 | 2013-03-12 | Elena
2.15 | Deliver: Updated Team Schedule | monday | 2013-03-11 | 8am | Elena | submit on date | 2013-03-12 | Elena
| email elaine re: submission | monday | 2013-03-11 | 8am | Elena |  | 2013-03-12 | Elena
https://sites.google.com/site/organizeyourteam/task-3-implement-use-case-1
3.1 | Write test code for Use Case #1 (see website) | Tuesday | 2013-03-12 | 6pm | Anaga | 18 | 2013-03-15 | Elena
3.2 | Write code of User Case 1 only | Tuesday | 2013-03-12 | 6pm | Satyen | 18 | 2013-03-13 | Satyen
3.3 | Feedback on code | wednesday | 2013-03-13 | 5pm | Anaga, Elena | 21 | 2013-03-15 | Anaga,Elena
3.4 | Review Source Code for clear comments, program guidelines | wednesday | 2013-03-13 | 5pm | Satyen | 21 | 2013-03-15 | Satyen
3.5 | Deliver: Draft 1 of Source Code to Elaine | Thursday | 2013-03-13 | 8am | Elena | 22, 23 | 2013-03-16 | Elena
| email elaine re: submission | thursday | 2013-03-13 | 8am | Elena |  | 2013-03-16 | Elena
3.6 | Update Design Document following Comments, if applicable | Thursday | 2013-03-13 | 9pm | Anaga | 24 | 2013-03-16 | no updates necessary
3.7 | Review Updated Design Document | Thursday | 2013-03-14 | 10pm | Satyen, Elena | 25 | 2013-03-16 | n/a
3.8 | Deliver: Final Draft of Source Code to Elaine | Friday | 2013-03-15 | noon | Anaga | 27
3.9 | Deliver: Run of Test Code | Friday | 2013-03-15 | noon | Anaga | 20, 24
3.1 | Deliver: Updated Design Document | Friday | 2013-03-15 | noon | Satyen | 27
3.11 | Deliver: Updated Team Schedule | Friday | 2013-03-15 | noon | Elena | submit on date
| email elaine re: submission | Friday | 2013-03-15 | noon | Anaga
2.16 | PRESENT TASK 2 AT TELECONFERENCE | Thursday | 2013-03-14 | 6pm | Elena with help from all
https://sites.google.com/site/organizeyourteam/task-4-implement-complete-program
4.1 | Write code for User Case 2 | Sunday | 2013-03-17 | 9pm | Satyen | task 3
4.2 | Write code for User Case 3 | Sunday | 2013-03-17 | 9pm | Anaga | task 3
4.3 | Write code for User Case 4 | sunday | 2013-03-17 | 9pm | Elena | task 3
4.4 | Write code for User Case 5 | sunday | 2013-03-17 | 9pm | Satyen | task 3
4.5 | Review all source code for clear comments, program guidelines | monday | 2013-03-18 | 6pm | Satyen | 31, 32, 33, 34
4.6 | Finalize Source Code (includes review of each User Case) | monday | 2013-03-18 | 9pm | All | 31, 32, 33, 34
4.7 | Update Design Document to reflect any changes | tuesday | 2013-03-19 | noon | Anaga | 35, 36
4.8 | Deliver: Run of Test Code | tuesday | 2013-03-19 | noon | Elena | 36
4.9 | Deliver: Source Code | tuesday | 2013-03-19 | noon | Elena | 36
4.1 | Deliver: Updated Design Document | tuesday | 2013-03-19 | noon | Anaga | 37
4.11 | Deliver: Updated Team Schedule | tuesday | 2013-03-19 | noon | Elena | submit on date
| email elaine re: submission | tuesday | 2013-03-19 | noon

## Meeting Schedule
Team Meetings
# | Topic | DoW | Date | Time | Anaga | Elena | Satyen
1 | Intro/Contract/Schedule | Sunday | 2013-03-03 | 9am | yes | yes | yes
2 | Intro to Git, Task 3 Review | Tuesday | 2013-03-05 | 8pm | yes | yes | yes
3 | Task 2 Overview | Thursday | 2013-03-07 | 6pm | yes | yes | yes
4 | Task 3 Review | Tuesday | 2013-03-12 | 8pm
5 | Task 3 Overview | Thursday | 2013-03-14 | 8pm
6 | Task 4 | Tuesday | 2013-03-19 | 8pm
More meetings scheduled as necessary.